## Instructions
Overview
This workbook provides multiple template options for managing both product backlogs and sprint backlogs. Select the templates you prefer--select one product backlog template (option 1, 2 or 3) and one sprint backlog template (1 week or 2 week) -- and then delete the others. Below are instructions on how to use each template, including which fields are editable, which are not, and issues to be aware of as you make modifications.
Product Backlog Instructions
Note: Each of the three product backlog templates use conditional formatting rather than visual basic (VBA) programming to avoid the use of macros in the Excel file, which can be problematic for some users in certain environments. The product backlog template options provide the data and calculations to not only generate a project/release burndown chart, but also to provide empirical "PERT" extrapolations for release delivery dates based on a scrum team's velocity. The three template options are identical, with the following differences (provided for individual preferences): Product Backlog - option 1: This option highlights all rows within the ranges calculated in columns K, L and M. Product Backlog - option 2: This option highlights only the last row of the ranges calculated in columns K, L and M. Product Backlog - option 3: This option underlines only the last row of the ranges calculated in columns K, L and M. Extrapolation data is calculated in the range F2:M15, and assumes a project with 10 sprints. This can be modified, but remember that the burndown chart's data range must be manually updated to match any changes. "P" stands for "pessimistic" (i.e. lowest velocity), "ML" stands for "most likely" (i.e. average velocity"), and "O" stands for "optimistic" (i.e. highest velocity). Be aware that many cells contain values and/or formulas required to calculate other cells and/or the burndown chart. Comments are provided in each cell (or the first cell in a range) that requires manual updating by the user. Avoid changing values in any cells that do not have a red flag in the upper right corner, indicating there is a comment.
Sprint Backlog Instructions
The product backlog template options provide the data and calculations to generate a sprint burndown chart for both story points and task hours. For instructions, see https://platinumedge.com/blog/anatomy-sprint-backlog. The two template options are identical, except for sprint length. Burndown chart data is generated based on data in rows 81-84. Rows can be deleted or added for tasks in each user story, however be aware that formulas may have to be updated in these rows, as well as in each individual user story row. Be aware that many cells contain values and/or formulas required to calculate other cells and/or the burndown chart. Avoid changing values in any cells that contain formulas.

## Product Backlog - option 1
<Product Name> Release Projections |  |  | Requirement |  | Empirical PERT Calculations |  |  |  |  | P Scope | ML Scope | O Scope
|  |  | Improvement |  |  | Actual | Sprints | Actual | Plan | Remain | Remain | Remain
2016-10-27 | Project start |  | Maintenance |  | Sprint | Velocity | Remain | Burn | Burn | 10 | 10 | 10
7 | Sprint length (days) |  | Overhead |  | Start | 10 | 10 | 142 | 142 | 100 | 100 | 100
3 | Release 1 sprints (#) |  |  |  | 1 |  | 9 | 142 | 127.8 | 90 | 90 | 90
7 | Release 1 release sprint length (days) |  |  |  | 2 |  | 8 | 142 | 113.6 | 80 | 80 | 80
2016-11-24 | Release 1 date |  |  |  | 3 |  | 7 | 142 | 99.4 | 70 | 70 | 70
2 | Release 2 sprints (#) |  |  |  | 4 |  | 6 | 142 | 85.2 | 60 | 60 | 60
0 | Release 2 release sprint length (days) |  |  |  | 5 |  | 5 | 142 | 71 | 50 | 50 | 50
2016-12-08 | Release 2 date |  |  |  | 6 |  | 4 | 142 | 56.8 | 40 | 40 | 40
3 | Release 3 sprints (#) |  |  |  | 7 |  | 3 | 142 | 42.6 | 30 | 30 | 30
0 | Release 3 release sprint length (days) |  |  |  | 8 |  | 2 | 142 | 28.4 | 20 | 20 | 20
2016-12-29 | Release 3 date |  |  |  | 9 |  | 1 | 142 | 14.2 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 142 | 0 | 0 | 0 | 0
<Product Name> Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size | Total | Completed | Dates | Goals
2 | <PBI title> | As a ____, I want ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | 2
3 | <PBI title> |  |  |  | 1 | 3
4 | <PBI title> |  |  |  | 3 | 6
5 | <PBI title> |  |  |  | 3 | 9
1 | <PBI title> |  |  |  | 5 | 14
6 | <PBI title> |  |  |  | 3 | 17
7 | <PBI title> |  |  |  | 2 | 19
8 | <PBI title> |  |  |  | 8 | 27
9 | <PBI title> |  |  |  | 5 | 32
10 | <PBI title> |  |  |  | 3 | 35
11 | <PBI title> |  |  |  | 3 | 38 |  | 2016-11-24 | Release 1: <goal>
13 | <PBI title> |  |  |  | 5 | 43
15 | <PBI title> |  |  |  | 5 | 48
14 | <PBI title> |  |  |  | 8 | 56
16 | <PBI title> |  |  |  | 5 | 61
20 | <PBI title> |  |  |  | 13 | 74 |  | 2016-12-08 | Release 2 <goal>
19 | <PBI title> |  |  |  | 13 | 87
17 | <PBI title> |  |  |  | 21 | 108
18 | <PBI title> |  |  |  | 34 | 142 |  | 2016-12-29 | Release 3 <goal>
22 | <PBI title> |  |  |  | 34 | 176
24 | <PBI title> |  |  |  | 21 | 197
25 | <PBI title> |  |  |  | 34 | 231
26 | <PBI title> |  |  |  | 13 | 244
27 | <PBI title> |  |  |  | 55 | 299
28 | <PBI title> |  |  |  | 89 | 388
29 | <PBI title> |  |  |  | 55 | 443
30 | <PBI title> |  |  |  | 34 | 477
31 | <PBI title> |  |  |  | 55 | 532
32 | <PBI title> |  |  |  | 21 | 553
34 | <PBI title> |  |  |  | 13 | 566
35 | <PBI title> |  |  |  | 55 | 621
36 | <PBI title> |  |  |  | 144 | 765
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Product Backlog - option 2
<Product Name> Release Projections |  |  | Requirement |  | Empirical PERT Calculations |  |  |  |  | P Scope | ML Scope | O Scope
|  |  | Improvement |  |  | Actual | Sprints | Target | Plan | Remain | Remain | Remain
2016-10-27 | Project start |  | Maintenance |  | Sprint | Velocity | Remain | Burn | Burn | 10 | 10 | 10
7 | Sprint length (days) |  | Overhead |  | Start | 10 | 10 | 142 | 142 | 100 | 100 | 100
3 | Release 1 sprints (#) |  |  |  | 1 |  | 9 | 142 | 127.8 | 90 | 90 | 90
7 | Release 1 release sprint length (days) |  |  |  | 2 |  | 8 | 142 | 113.6 | 80 | 80 | 80
2016-11-24 | Release 1 date |  |  |  | 3 |  | 7 | 142 | 99.4 | 70 | 70 | 70
2 | Release 2 sprints (#) |  |  |  | 4 |  | 6 | 142 | 85.2 | 60 | 60 | 60
0 | Release 2 release sprint length (days) |  |  |  | 5 |  | 5 | 142 | 71 | 50 | 50 | 50
2016-12-08 | Release 2 date |  |  |  | 6 |  | 4 | 142 | 56.8 | 40 | 40 | 40
3 | Release 3 sprints (#) |  |  |  | 7 |  | 3 | 142 | 42.6 | 30 | 30 | 30
0 | Release 3 release sprint length (days) |  |  |  | 8 |  | 2 | 142 | 28.4 | 20 | 20 | 20
2016-12-29 | Release 3 date |  |  |  | 9 |  | 1 | 142 | 14.2 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 142 | 0 | 0 | 0 | 0
<Product Name> Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size | Total | Completed | Dates | Goals
2 | <PBI title> | As a ____, I want ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | 2
3 | <PBI title> |  |  |  | 1 | 3
4 | <PBI title> |  |  |  | 3 | 6
5 | <PBI title> |  |  |  | 3 | 9
1 | <PBI title> |  |  |  | 5 | 14
6 | <PBI title> |  |  |  | 3 | 17
7 | <PBI title> |  |  |  | 2 | 19
8 | <PBI title> |  |  |  | 8 | 27
9 | <PBI title> |  |  |  | 5 | 32
10 | <PBI title> |  |  |  | 3 | 35
11 | <PBI title> |  |  |  | 3 | 38 |  | 2016-11-24 | Release 1: <goal>
13 | <PBI title> |  |  |  | 5 | 43
15 | <PBI title> |  |  |  | 5 | 48
14 | <PBI title> |  |  |  | 8 | 56
16 | <PBI title> |  |  |  | 5 | 61
20 | <PBI title> |  |  |  | 13 | 74 |  | 2016-12-08 | Release 2: <goal>
19 | <PBI title> |  |  |  | 13 | 87
17 | <PBI title> |  |  |  | 21 | 108
18 | <PBI title> |  |  |  | 34 | 142 |  | 2016-12-29 | Release 3: <goal>
22 | <PBI title> |  |  |  | 34 | 176
24 | <PBI title> |  |  |  | 21 | 197
25 | <PBI title> |  |  |  | 34 | 231
26 | <PBI title> |  |  |  | 13 | 244
27 | <PBI title> |  |  |  | 55 | 299
28 | <PBI title> |  |  |  | 89 | 388
29 | <PBI title> |  |  |  | 55 | 443
30 | <PBI title> |  |  |  | 34 | 477
31 | <PBI title> |  |  |  | 55 | 532
32 | <PBI title> |  |  |  | 21 | 553
34 | <PBI title> |  |  |  | 13 | 566
35 | <PBI title> |  |  |  | 55 | 621
36 | <PBI title> |  |  |  | 144 | 765
765
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Product Backlog - option 3
<Product Name> Release Projections |  |  | Requirement |  | Empirical PERT Calculations |  |  |  |  | P Scope | ML Scope | O Scope
|  |  | Improvement |  |  | Actual | Sprints | Target | Plan | Remain | Remain | Remain
2016-10-27 | Project start |  | Maintenance |  | Sprint | Velocity | Remain | Burn | Burn | 10 | 10 | 10
7 | Sprint length (days) |  | Overhead |  | Start | 10 | 10 | 142 | 142 | 100 | 100 | 100
3 | Release 1 sprints (#) |  |  |  | 1 |  | 9 | 142 | 127.8 | 90 | 90 | 90
7 | Release 1 release sprint length (days) |  |  |  | 2 |  | 8 | 142 | 113.6 | 80 | 80 | 80
2016-11-24 | Release 1 date |  |  |  | 3 |  | 7 | 142 | 99.4 | 70 | 70 | 70
2 | Release 2 sprints (#) |  |  |  | 4 |  | 6 | 142 | 85.2 | 60 | 60 | 60
0 | Release 2 release sprint length (days) |  |  |  | 5 |  | 5 | 142 | 71 | 50 | 50 | 50
2016-12-08 | Release 2 date |  |  |  | 6 |  | 4 | 142 | 56.8 | 40 | 40 | 40
3 | Release 3 sprints (#) |  |  |  | 7 |  | 3 | 142 | 42.6 | 30 | 30 | 30
0 | Release 3 release sprint length (days) |  |  |  | 8 |  | 2 | 142 | 28.4 | 20 | 20 | 20
2016-12-29 | Release 3 date |  |  |  | 9 |  | 1 | 142 | 14.2 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 142 | 0 | 0 | 0 | 0
<Product Name> Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size | Total | Completed | Dates | Goals
2 | <PBI title> | As a ____, I want ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | 2
3 | <PBI title> |  |  |  | 1 | 3
4 | <PBI title> |  |  |  | 3 | 6
5 | <PBI title> |  |  |  | 3 | 9
1 | <PBI title> |  |  |  | 5 | 14
6 | <PBI title> |  |  |  | 3 | 17
7 | <PBI title> |  |  |  | 2 | 19
8 | <PBI title> |  |  |  | 8 | 27
9 | <PBI title> |  |  |  | 5 | 32
10 | <PBI title> |  |  |  | 3 | 35
11 | <PBI title> |  |  |  | 3 | 38 |  | 2016-11-24 | Release 1: <goal>
13 | <PBI title> |  |  |  | 5 | 43
15 | <PBI title> |  |  |  | 5 | 48
14 | <PBI title> |  |  |  | 8 | 56
16 | <PBI title> |  |  |  | 5 | 61
20 | <PBI title> |  |  |  | 13 | 74 |  | 2016-12-08 | Release 2: <goal>
19 | <PBI title> |  |  |  | 13 | 87
17 | <PBI title> |  |  |  | 21 | 108
18 | <PBI title> |  |  |  | 34 | 142 |  | 2016-12-29 | Release 3: <goal>
22 | <PBI title> |  |  |  | 34 | 176
24 | <PBI title> |  |  |  | 21 | 197
25 | <PBI title> |  |  |  | 34 | 231
26 | <PBI title> |  |  |  | 13 | 244
27 | <PBI title> |  |  |  | 55 | 299
28 | <PBI title> |  |  |  | 89 | 388
29 | <PBI title> |  |  |  | 55 | 443
30 | <PBI title> |  |  |  | 34 | 477
31 | <PBI title> |  |  |  | 55 | 532
32 | <PBI title> |  |  |  | 21 | 553
34 | <PBI title> |  |  |  | 13 | 566
35 | <PB title> |  |  |  | 55 | 621
36 | <PB title> |  |  |  | 144 | 765
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Sprint Backlog - 1 week option
<Product name> - Sprint <#>
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 4.5
Sprint Goal | [6 empty] | M | Tu | W | Th | F | Total
Demonstrate the ability to <sprint goal>. (NOTE: Define a sprint goal in terms of working customer functionality you will be able to demonstrate to internal stakeholders and possibly release to the marketplace.) | [5 empty] | Developers | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[11 empty] | Total sprint hours: | 130
[11 empty] | Total per day: | 28.8889
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 8 | Developer name | 8 | 8 | 8 | 8 | 8
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 5 | Developer name | 5 | 5 | 5 | 5 | 5
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 3 | Developer name | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | Developer name | 2 | 2 | 2 | 2 | 2
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 1 | Developer name | 1 | 1 | 1 | 1 | 1
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
Actual Hrs Remaining | [6 empty] | 120 | 120 | 120 | 120 | 120
Schedule Hrs Remaining | [6 empty] | 130 | 97.5 | 65 | 32.5 | 0
Story Points Remaining | [6 empty] | 19 | 19 | 19 | 19 | 19
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5
Issues
Team Member
<issue>
Team Member
<issue>
<issue>

## Sprint Backlog - 2 week option
<Product name> - Sprint <#>
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 9
Sprint Goal | [6 empty] | M | Tu | W | Th | F | M | T | W | Th | F | Total
Demonstrate the ability to <sprint goal>. (NOTE: Define a sprint goal in terms of working customer functionality you will be able to demonstrate to internal stakeholders and possibly release to the marketplace.) | [5 empty] | Developers | <DD> Sprint Planning | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> Sprint Review + Retrospective
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[16 empty] | Total sprint hours: | 260
[16 empty] | Total per day: | 28.8889
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F | M | T | W | Th | F
ID | Task |  |  | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 8 | Developer name | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 5 | Developer name | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 3 | Developer name | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | Developer name | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 1 | Developer name | bar: M to F
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual Hrs Remaining | [6 empty] | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Schedule Hrs Remaining | [6 empty] | 260 | 231.1111 | 202.2222 | 173.3333 | 144.4444 | 115.5556 | 86.6667 | 57.7778 | 28.8889 | 2.1316e-14
Story Points Remaining | [6 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Issues
Team Member
<issue>
Team Member
<issue>
<issue>